## Front Pages
DRAFT
Schedule of Dilapidations
of
315-317 Sauchiehall Street,
Glasgow,
B-Listed Building (315–349 Sauchiehall Street)
G81 1LQ
November 2025
General clauses and preliminaries
This is a Schedule of Dilapidations prepared for the Premises known as 173/175 Glasgow Road, Clydebank, Glasgow G81 1LQ. The Schedule identifies the Wants of Repair found at the Premises under the terms of the Lease dated 20th July 1999 entered into between Thomas George Baker and Mrs Myra Elizabeth Baker residing at 19 Collylin Road, Bearsden, Glasgow G61, the Managing Trustees acting under and in terms of the TG Baker (Sound) Limited Directors Trust Deed dated 31st March 1999 and their successors as Trustees under and in terms of Declaration of Trust dated 31st March 1999 whose interests are now vested in Standard Life Trustee Company Limited (“The Landlord”), and T G BAKER (SOUND) LIMITED (Company Number SCO53364) having their registered office at 173/175 Glasgow Road, Clydebank, G81 1LQ (“the Tenant”).
1) | The Premises comprise the subjects known as 173 / 175 Glasgow Road, Clydebank, Glasgow, G81 1LQ.
2) | For the purposes of this Schedule, the front elevation of the Premises, facing Glasgow Road, is assumed to face south.
3) | The Schedule identifies the Wants of Repair identified at the Premises at the time of the survey by the Landlord's Surveyor. The Landlord reserves the right to add to or amend the Schedule as further defects become apparent.
4) | The final selection of finishes including all colours, specifications etc. are subject to approval by the Landlord. The specification for all paint finishes including number of coats, type of finishes etc. must be appropriate for the works required, be in accordance with good practice and to the satisfaction of the Landlord.
5) | The Schedule identifies repairs required to make good the defects listed. Further works may be necessary to remedy the defect listed due to further defects being unforeseen, covered by Tenant fittings or otherwise concealed and these works are deemed to be included in the Schedule.
6) | The Tenant is responsible for ensuring that the specification for all works is appropriate and ensuring works carried out meet with the approval of the Landlord.
7) | We have not expressed an opinion on those parts of the Property that were covered, unexposed or were inaccessible at the time of our inspection. Should defects in these areas become apparent later then they are deemed to be included in the Schedule.
8) | We were not able to access some of the office and other areas during our inspection. These are listed on the report.

## External
Item No | Lease clause | Want of repair | Remedy | U | Q | R | £
1 |  | Rear Elevation
1.01 | One, Two, Three | Three holes through stonework to rear elevation. | Cut out defective areas; indented matching stone plugs; repoint with lime mortar; make good. | Sum |  |  | 600
1.02 | Two, Four | Rear timber fire door and frame require redecoration. | Prepare and redecorate door, frame and surround with undercoat and two coats gloss. | Sum |  |  | 180
1.03 | Three | Concrete step to rear fire door is cracked and deteriorating. | Break out loose areas; repair and reface with polymer-modified concrete; make good falls. | Sum |  |  | 350
Shopfront (Front Elevation)
2.01 | Seven, Two, Four | Signage, vinyls and graffiti to shopfront; timber fascia/frames weathered and local decay; cracked tile; defective lead flashing. | Remove all signage/vinyls; clean glazing; replace broken tile; renew lead flashing to fascia; repair decayed timber; prepare and redecorate shopfront and entrance door; service ironmongery. | Sum |  |  | 3000
Total for Collection

## Ground Floor
Item No | Lease clause | Want of repair | Remedy | U | Q | R | £
5 |  | Rear Store Area
5.01 | Two, Four | Plasterboard ceiling stained with redundant fittings and poor cable hole. | Remove redundant fittings; infill and make good; install new LED batten; redecorate ceiling. | Sum |  |  | 450
5.02 | Two | Walls scratched with fixing/bolt holes. | Remove bolts; fill and make good; redecorate throughout. | m² | 40 | 8
5.03 | Three | Laminate sheet flooring marked and soiled. | Uplift and dispose; supply and lay new commercial vinyl. | m² | 30 | 25
5.04 | Two | uPVC skirting to perimeter to be replaced with flooring change. | Remove and replace to match new flooring. | m | 35 | 6
5.05 | Two | Four internal timber doors scratched/with fixing holes; damaged frame to electrical room. | Repair frames; make good holes; fit new ironmongery; redecorate doors and frames. | No | 4 | 120
5.06 | Three | Security cameras, speakers and mechanical ventilation grilles to be removed and made good. | Remove installations and make good penetrations/finishes. | Sum |  |  | 400
5.07 | Seven | Timber stud partitions and all desks/shelving to be removed. | Strip out partitions, counters, tables and shelving; make good. | Sum |  |  | 900
Electrical Cupboard
5.08 | Two | Suspended ceiling grid deformed with missing tiles; vandalised light fitting. | Renew grid and tiles; replace light fitting; make good. | Sum |  |  | 600
5.09 | Two | Walls marked with nails. | Make good all damage and redecorate. | m² | 15 | 8
5.1 | Three | Timber boarded floor marked and soiled. | Deep clean and reseal. | m² | 10 | 6
5.11 | Three | Loose cable present. | Remove safely and make good. | Sum |  |  | 80
WC (Rear)
5.12 | Two | Ceiling requires redecoration; replace light fitting. | Redecorate ceiling and install new sealed LED bulkhead. | Sum |  |  | 220
5.13 | Two | Ceramic tiled walls with soiled grout and local damage, one tile missing. | Regrout; replace damaged/missing tiles; clean down. | Sum |  |  | 250
5.14 | Two | Vinyl timber-effect floor damaged; water heater on floor. | Replace vinyl; lift cylinder on proper bracket; install threshold. | Sum |  |  | 380
5.15 | Three | Door without lock/ironmongery; frames/skirts to redecorate. | Fit new lock/ironmongery and redecorate joinery. | Sum |  |  | 150
Main Sales Area
5.16 | Two | Plasterboard ceiling soiled with large holes and redundant lights. | Patch with plasterboard incl. 0.4x1.0m and 0.5x1.0m repairs; remove redundant fittings; redecorate. | Sum |  |  | 1200
5.17 | Seven | Laminate wall panels to SE corner scratched/holed. | Strip laminate and replace new; make good substrate; redecorate. | m² | 20 | 35
5.18 | Seven | Metal wall panelling/shelving and timber supports to south/east/west walls. | Remove all linings and shelving; make good walls and redecorate. | Sum |  |  | 950
5.19 | Three | Vinyl laminate floor throughout damaged and taped. | Remove and replace with new commercial vinyl; remove decals. | m² | 120 | 25
5.2 | Three | uPVC skirting to match flooring renewal. | Remove and replace with new. | m | 120 | 6
5.21 | Seven | Remove services: 5x speakers, 6x CCTV, 7x ventilation grilles/panels; clean/ service 3 access hatches. | Remove/label and make good; clean and service access hatches. | Sum |  |  | 700
5.22 | Seven | Counter and raised floor behind incl. 5m length; large desk to NW. | Remove counter, raised floor and desk; make good floor/finishes. | Sum |  |  | 1000
5.23 | Three | Defective raised platform (3x3m) to NW corner. | Remove platform and make good sub-floor level. | Sum |  |  | 350
5.24 | Four | Shopfront internal surrounds/door scratched. | Clean glazing; prepare and redecorate surrounds and entrance door. | Sum |  |  | 300
Stairwell and Corridor
5.25 | Two | Stairwell lacks ceiling/plaster to GF; PB to basement to be cleaned and redecorated; remove partitions/door. | Remove partitions/door; install/repair plasterboard where required; redecorate. | Sum |  |  | 900
5.26 | Three | Flooring to stair/corridor worn; nosings marked. | Replace laminate/vinyl and nosings; clean and redecorate handrail/stringer. | Sum |  |  | 950
5.27 | Two | Corridor PB ceiling and walls soiled with holes; faulty downlighters. | Clean, infill and redecorate; replace faulty downlighters. | Sum |  |  | 400
Stores and Bedrooms (Lower Ground)
5.28 | Two | Electrical store: clean/redecorate walls/ceiling; replace deteriorated west wall lining; repair impact to east; remove debris; scarify floor; fit missing DB cover. | Undertake works as described. | Sum |  |  | 850
5.29 | Two | Store room: mould/soiling to ceiling; remove 2 speakers; clean 12 fittings and replace emergency fitting; redecorate walls and skirting; service/remove wall fan; replace missing/damaged vinyl floor; remove rubbish; provide new door. | Undertake works as described. | Sum |  |  | 1600
5.3 | Two | Rear bedroom: non-compliant fire door and frame to redecorate; walls/ceiling to clean and repair; remove tiled band 5x0.5m; remove whiteboards and heater; new skirting to east; replace carpet tiles. | Undertake works as described and provide new LED light and service MV. | Sum |  |  | 2100
5.31 | Two | Men’s toilet: redecorate ceiling/walls; replace defective lights; service MV; replace vinyl; clean/service sanitaryware; replace 4 downlighters; renew skirtings with flooring. | Undertake works as described. | Sum |  |  | 1800
5.32 | Two | Female toilet: as male; 2 downlighters broken. | Undertake same scope as men’s with repairs. | Sum |  |  | 1500
5.33 | Two | Rear store at end: redecorate PB ceiling/walls and timber skirtings; replace laminate floor; remove desk; replace emergency light. | Undertake works as described. | Sum |  |  | 1200
Total for Collection

## First Floor
Item No | Lease clause | Want of repair | Remedy | U | Q | R | £
Total for Collection

## General Items
Item No | Lease clause | Want of repair | Remedy | U | Q | R | £
Total for Collection

## Collection
Item No |  |  | £
COLLECTION
External
Ground Floor
First Floor
General Items
Sub total
| Contractor preliminaries | Allow 20%
Sub Total of work items
Professional fees for managing the works
| Contract administration | Allow 10%
| Mechanical and electrical engineer | Allow 0%
| Principal Designer | Allow 1%
Sub Total
| Professional Fees (exc. VAT) for preparation of Schedule of Dilapidations (Building Surveyor) |  | 1750
| Professional Fees (exc. VAT) for Negotiation of Settlement | Allow 5%
GRAND TOTAL EXCLUDING VAT